# FNPW Website Go-Live Playbook

For: Elycia. Assumes: 1.5 hrs per day, every day or second day (about 6 hrs/week). Written: July 2026. This document is designed to be self-sufficient: everything Claude worked out about this project is captured here, so any future Claude session (or a human developer) can pick up from any point. When starting a new Claude session, paste the relevant week's section and say "continue from here".

## 1. The rules (read first, they prevent disasters)

- Never build on the live site. All theme and plugin work happens on the SiteGround staging copy. The live site only changes at launch, and via normal content publishing.

- Code flows up, content flows down. Code: local repo → staging → production. Content: created on production (or staging just before launch), never re-keyed twice. WordPress databases cannot be merged; plan so you never need to.

- Backup before anything scary. UpdraftPlus full backup before plugin updates, theme activation, or launch. Check the backup actually completed.

- Commit after every session. git add -A && git commit -m "what changed" in the website-project folder. Git is the undo button.

- Launch freeze windows: never switch themes in June (EOFY) or November-December (Gift a Tree, 12 Days of Wildlife). If you miss the October window, hold until February.

- Cultural content: RAP, Kaurna and Firesticks material is ported verbatim, never rewritten, and any change needs sign-off through the existing approval process. Always "Kaurna Yarta". Always "&" in the organisation name. No em dashes.

- Donations stay on Raisely for this launch. Donate buttons keep their existing hrefs. Payments migration (GiveWP) is phase 2, after the site is stable.

## 2. Inventory: what exists and where

The repo (~/Downloads/website-project, branch consolidate):

- 121 HTML pages: 13 originals + 83 project pages + 3 pillar pages + ~20 site pages

- assets/css/global.css - the whole design system (tokens + components), one file

- assets/js/main.js - shared JS; partials/ - header + footer (canonical)

- data/projects.json - all 83 projects: slug, title, image, pillar (provisional), state

- tools/sync.py - edit a partial, run this, all pages update

- tools/gen_projects.py, gen_pages.py, gen_exemplars.py - page generators (re-runnable)

- tools/make_design_pack.py - rebuilds design/ single-file templates

- design/ - 8 template files + DESIGN-BRIEF.md + CLAUDE-DESIGN-PROMPT.md

- Exemplar pages with full real content: project-warddeken-mayh.html (long), project-remarkable-southern-flinders.html (medium), project-southern-highlands-koala-conservation.html (short)

- Preview: python3 -m http.server 8000 in the folder, open http://localhost:8000

The live stack (fnpw.org.au):

- WordPress on SiteGround (staging available in Site Tools), custom fnpw theme (Sage/Blade, locked) + Elementor 4.x for page layouts

- "Template Required Plugins" (by drufloe) registers the project post type, taxonomies project_state, project_focus_area, project_year, plus grant and donation types. THIS IS CRITICAL: the new build must reuse these exact post type keys.

- ACF Pro 6.8 installed and active. Yoast SEO (Premium subscription EXPIRED, free still works). Redirection plugin installed. UpdraftPlus backups. Formidable Forms + HubSpot (newsletter/EDM) + Post SMTP (email delivery).

- Analytics: Google Tag Manager container GTM-K2P27RG. Keep it through launch.

- Donations: Raisely, hosted off-site (foundation-for-national-parks-and-wildlife.raiselysite.com, habitat-heroes.raiselysite.com, bush.fnpw.org.au, gift-a-tree.fnpw.org.au subdomain).

- 85 live project URLs under /project/<slug>/ (2 are junk/grants, see redirects).

- Org facts: ABN 90 107 744 771, 1800 898 626, GPO Box 2666 Sydney NSW 2001, ACNC registered, DGR endorsed.

Known issues to fix along the way: 29 plugins pending updates with auto-update off; AccessPress Anonymous Post Pro must be DELETED (compromised vendor, powers the junk upload-your-blog-post page); 7 inactive plugins to delete; Akismet unconfigured; decide renew-or-drop Yoast Premium (Redirection covers redirects, so dropping is fine); live og:locale says en_US, should be en_AU.

## 3. Week by week

Sessions are ~1.5 hrs. "Prompt" lines are what to paste into Claude (with relevant files).

### Week 1 (wc 6 Jul) - Foundations and cleanup, part 1

- Session 1: Email REEF/host contacts: confirm no contractual barrier to self-managed theme; confirm who owns the SiteGround account and get Site Tools access. Subscribe to Claude Max (5x) if not already.

- Session 2: UpdraftPlus full backup (verify it completed). Then in Plugins: DELETE AccessPress Anonymous Post Pro, and the inactive seven (Wordfence*, WP Rocket, Smush, reSmush, Image Optimizer, Autoptimize, Search & Replace). *Optional: activate Wordfence once first and run a malware scan, then delete.

- Session 3: Update all plugins EXCEPT Elementor (backup first, update in batches of five, check the site loads after each batch). Configure Akismet (free key).

- Done when: backup verified, cruft gone, updates applied, access confirmed.

### Week 2 (wc 13 Jul) - Staging + pillar data

- Session 1: SiteGround Site Tools > WordPress > Staging > Create. Update Elementor on staging, check key pages, then repeat on live. In staging wp-admin, open the "Template Required Plugins" code (Plugins > Plugin File Editor) and copy the register_post_type / register_taxonomy code into a file for Claude. This tells us the exact CPT keys.

- Session 2: Review data/projects.json: correct the pillar guess for every project you know (43 species / 28 healing / 12 parks currently, all marked unconfirmed). Ask Claude to regenerate pages after edits: python3 tools/gen_projects.py && python3 tools/gen_exemplars.py && python3 tools/sync.py.

- Session 3: Sweep the yellow "To port from live site" boxes: copy-paste real copy from the live pages into a single notes file (or give Claude the live URLs and ask it to port them into the static pages the way the exemplars were done).

- Done when: staging exists, CPT registration code captured, pillars corrected.

### Weeks 3-5 (wc 20 Jul - 9 Aug) - Design

- One Claude design session per sitting, in this order: index, projects hub, project detail (warddeken), pillar page, campaign, donate, about, simple content page.

- Use design/CLAUDE-DESIGN-PROMPT.md + attach the brand guidelines PDF + ONE file from design/. From session 2 onward also attach the approved homepage as reference.

- After each session, bring the returned file to Claude (Cowork) with: Prompt: "Here is the redesigned template from Claude design. Diff it against the original in design/, merge the changed CSS into assets/css/global.css (and partials if the header/footer changed), run tools/sync.py, and show me what changed."

- Done when: all 8 templates approved and merged; whole 121-page site restyled; commit.

### Weeks 6-9 (wc 10 Aug - 6 Sep) - WordPress theme build (on staging only)

This is the part you haven't done before. It is a mechanical translation, not a redesign.

- Session 1 (scaffold): Prompt: "Build a classic WordPress theme called fnpw2026 from this static site. Here are partials/header.html, partials/footer.html, assets/, and index.html. Produce: style.css (theme header comment), functions.php (enqueue global.css, main.js and Google fonts; register a primary menu; add theme supports), header.php and footer.php (from the partials, with wp_head()/wp_footer() and home_url() links), front-page.php (from index.html), page.php (generic content template). Zip layout ready for upload." Upload via staging wp-admin > Appearance > Themes > Add New > Upload. Activate ON STAGING. Expect it to look right but with dead links; that is fine.

- Session 2 (content plugin): Prompt: "Here is the register_post_type code from the current site's Template Required Plugins. Write a small standalone plugin, fnpw-content, that registers the SAME post type keys and slugs for project (and keeps grant/donation types readable), plus a new public 'pillar' taxonomy (growing-national-parks, saving-species, healing-the-land) attached to project. It must not conflict if the old plugin is active; guard with post_type_exists()." Install on staging, then deactivate the old drufloe plugin and confirm all projects are still visible in wp-admin and at /project/... If anything vanishes, reactivate the old one and debug with Claude.

- Session 3 (ACF): In staging: ACF > add field groups for Projects (year, state, status, latitude, longitude, stats repeater, gallery, lead partner) and an Options page (contact details, ABN, donate URLs). Ask Claude for the import JSON instead of clicking it all: Prompt: "Generate an ACF Pro import JSON for these field groups... and tell me how to enable Local JSON (acf-json folder in the theme)."

- Sessions 4-6 (templates): Prompt: "Convert these static pages into theme templates wired to WordPress: single-project.php from project-warddeken-mayh.html (title, ACF fields, the_content, related projects by shared pillar term); taxonomy-pillar.php from saving-species.html (term title/description + WP_Query loop of that term's projects using the card markup); page templates for campaign and simple content pages; archive and search.php and 404.php. Replace hardcoded card grids with loops. Map pins: wp_localize_script an array of {title, lat, lng, url} from a WP_Query of projects." Iterate: upload, look, screenshot problems back to Claude.

- Session 7: Menus (Appearance > Menus, match the static nav), widgets/footer links, Yoast on the new templates, permalinks check (project URLs must not change).

- Done when: staging site renders the new design from the CMS: front page, a pillar page listing its projects from the taxonomy, warddeken renders from post content + ACF, menus work, old URLs resolve.

### Weeks 10-11 (wc 7 - 20 Sep) - Content

- Tag all 83 projects with their pillar term (data/projects.json is the source of truth; Claude can generate a WP-CLI or CSV import to do it in bulk, or do it manually, ~2 sessions).

- Set featured images (they are already in the media library from the old site).

- Port remaining yellow-box copy into WP pages. Recreate corporate volunteering city pages as CHILD pages of corporate-volunteering so URLs stay /corporate-volunteering/sydney/ (the static prototype flattened these; WordPress should not).

- Newsletter: paste the HubSpot form embed into the newsletter page and test a signup. Forms: rebuild/embed the Formidable contact + media forms, test submissions arrive.

- Done when: no yellow boxes remain on staging, forms tested, projects all tagged.

### Weeks 12-13 (wc 21 Sep - 4 Oct) - Quality

- Redirects (Redirection plugin), minimum set: /grants/ and /grant/wildlife-heroes-grants/ → /ways-you-can-get-involved/ (we no longer do grants); /project/form-test/, /test-form/, /upload-your-blog-post/ → 410 gone or → home; /project/bushfire-recovery-small-grants/, /private-land-conservation-grants/, /community-conservation-grants/ → /projects/ ; /paws-magazine/ → /news/ ; /tax-deductible-charity-donation/ → /donations/ ; /foundation-for-national-parks-and-wildlife-newsletter/ → /newsletters-sign-up/. Everything else keeps its URL by design, so no other redirects should be needed. Verify with Yoast that titles/metas carried over on key pages.

- Accessibility pass: keyboard-tab the nav, map and FAQ accordions; alt text sweep; contrast check anywhere wattle or light text was used. Fix og:locale to en_AU.

- Performance: run PageSpeed on staging URL; lazy-load confirmed; ask Claude to fix anything under ~85 mobile.

- Cross-browser/device: Safari, Chrome, an iPhone and an Android. Screenshot issues to Claude.

- Done when: the launch checklist below is all green ON STAGING.

### Week 14 (wc 5 Oct) - Launch (window A)

Decision gate: if this slips past 1 November, STOP. Keep staging warm, launch early February 2027 instead. Never switch during Gift a Tree season.

- Pre-flight (session 1): full UpdraftPlus backup of production (files + DB), download it. Confirm rollback plan: Appearance > Themes > activate old theme = instant undo.

- Launch (session 2, pick a quiet morning, Tue-Thu): SiteGround "push staging to live" (Site Tools does this) OR: upload fnpw2026 theme + fnpw-content plugin to production, activate plugin, activate theme, import acf-json, set menus, add redirects. Then immediately: click every nav item, make a $2 test donation via the donate page (refund it), submit the contact form, sign up to the newsletter, check GTM fires (Tag Assistant), check /project/warddeken-mayh/ and two other old URLs.

- Post-launch week: watch Redirection's 404 log daily and add redirects for anything real; check Search Console for coverage errors; monitor site speed and forms.

### Launch checklist (copy into an issue and tick)

- Backup taken and downloaded

- Old theme still installed (rollback path)

- All nav + footer links resolve

- Donate → Raisely works end to end (test gift)

- Newsletter signup reaches HubSpot

- Contact + media forms deliver email

- 5 sampled old project URLs return 200

- Redirect list live and tested

- GTM firing, GA receiving

- Yoast sitemap regenerated and submitted in Search Console

- 404 page, search page work

- Mobile spot-check on a real phone

- og:locale en_AU, favicons, social share cards look right

## 4. Canned prompts for future Claude sessions

- Context bootstrap: "You are helping me finish the FNPW website rebuild. Read PLAYBOOK.md and CLAUDE.md in this folder, then tell me where we are up to based on git log, and what this session should do. I have 1.5 hours."

- Debugging WP: "Here is the template file, the error/screenshot, and what I expected. Fix it and explain the change in one sentence." (Always paste the actual file.)

- Design merge: see Weeks 3-5.

- Bulk content: "Generate a WP-CLI script / CSV import to [task] using data/projects.json. I will run it on staging via SiteGround's WP-CLI in Site Tools."

- Security review (before launch): "Review fnpw2026 theme and fnpw-content plugin for escaping (esc_html/esc_url/wp_kses), nonces, and unsanitised input. List and fix issues."

## 5. Phase 2 backlog (after launch, not before)

- Donations on-site: GiveWP + Fee Recovery, one appeal first, recurring donors last; check whether Raisely runs on FNPW's own Stripe account before planning migration.

- Threatened Species Spotlight hub; blog category templates; Reports archive as CPT.

- Google Ad Grants application (US$10k/month free search ads for eligible charities).

- Retire Elementor once no live pages depend on it; drop Yoast Premium if not renewed.

- Delete the old fnpw theme after a stable month. Keep the drufloe plugin deactivated for a month before deleting.

- Handover: walk your colleague through this file + one publish + one deploy.

# FNPW Rebuild: What Can Go Wrong and How to Fix It

Companion to PLAYBOOK.md. Written for a non-developer. Read the Emergency Card now so you know it exists; read the rest when something happens (or before each phase).

The comforting truth first: the way this project is set up, the live site is very hard to break. All build work happens on a staging copy the public never sees. Donations run on Raisely, outside WordPress entirely, so no theme work can touch payment processing. The old theme stays installed, so the ultimate undo is Appearance > Themes > Activate old theme. Almost everything below is "staging looks broken", which costs you a session, not a website.

## EMERGENCY CARD: the live site is down or broken right now

- Don't panic-fix. Note what you did last (that is almost always the cause).

- If wp-admin still loads: Appearance > Themes > activate the OLD fnpw theme. Site back.

- If wp-admin won't load (white screen): log in to SiteGround > Site Tools > File Manager, go to wp-content/themes/, rename the new theme folder (e.g. fnpw2026 → fnpw2026-off). WordPress instantly falls back. Same trick for a broken plugin: rename its folder in wp-content/plugins/.

- Still broken: SiteGround Site Tools > Backups > restore the UpdraftPlus/SiteGround backup from before your change (you always made one, because Rule 3).

- Then paste whatever error you saw into Claude with "the live site broke when I did X".

## 1. WordPress build phase (weeks 6-9)

### White screen after activating the theme or plugin (on staging)

- Why: a PHP syntax error, usually in functions.php. One missing semicolon does this.

- Fix: rename the theme folder via File Manager (see Emergency Card) to get admin back. Then in Site Tools > Statistics/Logs (or ask Claude how to enable WP_DEBUG_LOG), copy the exact error line and paste it to Claude with the file. It is always a one-line fix.

- Prevent: never edit code through wp-admin's Theme File Editor. Edit locally, upload the whole file. Test every upload on staging immediately.

### All the projects vanished from wp-admin

- Why: the post type isn't registered right now. Deactivating the old "Template Required Plugins" before the new fnpw-content plugin registers the same key does this. The content is NOT deleted; it is sitting safely in the database, invisible.

- Fix: reactivate the old plugin; everything reappears. Then have Claude compare the register_post_type key and args in both plugins until they match exactly.

- Never run anything that offers to "clean up orphaned posts" while they are invisible.

### Every project page is a 404 after activating the plugin/theme

- Why: WordPress hasn't refreshed its URL rules. Looks catastrophic, is nothing.

- Fix: Settings > Permalinks > click Save Changes (change nothing). Do it twice.

### ACF fields don't appear on the edit screen, or show but don't display on the page

- Why (edit screen): the field group's Location rule doesn't match the post type.

- Why (front end): the template asks for a different field name than the field's actual name, or get_field() is called before ACF loads.

- Fix: screenshot the field group settings + paste the template to Claude.

### The map shows no pins

- Why: projects have no lat/lng values yet, or the data isn't reaching the JS.

- Fix: add coordinates to 2 test projects first, view page source, search for the localized data array, paste what you find to Claude.

### Images broken after theme switch on staging

- Fix: usually wrong image size names; ask Claude. If thumbnails are missing sizes, install "Regenerate Thumbnails", run once, delete it.

## 2. The one real catastrophe to understand: the staging push

SiteGround's "push staging to live" can copy the staging DATABASE over production. If people published news posts, edited pages, or received form entries on the live site while you were building on staging, a full push erases those newer changes. This is the single most expensive mistake available to you.

- Safe path (use this): do NOT full-push. Deploy manually: upload the theme zip and plugin zip to production, activate, import the acf-json, set menus, add redirects. Production database is never overwritten; nothing published is lost.

- If you do push: declare a content freeze (no publishing anywhere) from the moment you last refreshed staging until launch, and confirm SiteGround's push options: push files only if offered, or accept the freeze consciously.

- Either way: full backup downloaded to your computer first.

## 3. Working with Claude (the AI-shaped risks)

### The code Claude gives you doesn't work

- Paste back: the exact error text or a screenshot, the full file (not a fragment), and what you expected. Ask for "the smallest possible fix, explained in one sentence". Do not accept a rewrite of the whole file when debugging; small diffs are checkable.

### A session confidently "fixes" things and now more is broken

- Stop. git status / git diff shows what changed. git checkout -- <file> reverts a file; git reset --hard reverts everything uncommitted. This is why Rule 4 says commit after every good session: you can always step back to the last known-good state.

- Start a fresh session with the PLAYBOOK bootstrap prompt rather than arguing with a session that has gone down a bad path.

### You hit your usage limit mid-session

- Max limits reset every few hours. Commit what works, note where you stopped in a NOTES.md line, resume later. Never leave staging half-broken overnight without a note.

### Claude invents a WordPress function or plugin setting that doesn't exist

- If something errors as "undefined function", say exactly that; it will correct itself. For anything involving money, deletion, or the live database, ask: "is there a safer, more standard way to do this?" before running it.

## 4. Updates, plugins and the live site (ongoing)

### A plugin update breaks the live site

- Fix: File Manager > rename that plugin's folder > site returns > restore backup if needed. This is why updates happen in small batches with a check between, backup first, and Elementor-sized updates go to staging first.

### Locked out of wp-admin

- Security Optimizer or repeated failed logins can lock you out. Fix: SiteGround Site Tools can reset your WordPress password; or rename the security plugin's folder via File Manager, log in, rename it back.

### Forms stop sending email

- Post SMTP handles delivery; check its log first (it shows every send attempt). Test the contact form after any plugin update. Check spam folders before panicking.

### Staging isn't available on our SiteGround plan

- Staging needs GrowBig or higher. If the plan is StartUp: upgrade (small monthly cost, put it in the project budget) rather than building without staging. Do not build live.

## 5. Launch and after

### Rankings wobble after launch

- A small dip for 1-2 weeks is normal. What matters: Search Console shows no coverage errors, and Redirection's 404 log stays quiet. Add redirects for any real 404s that appear. Only consider rolling back for major, persistent loss, which the URL-preserving design makes very unlikely.

### Donate button goes to the wrong place / short links die

- Theme work cannot break Raisely itself. If a donate link 404s, it is just an href typo: fix the link. The bit.fnpw.org.au short links are a separate service; if they die, point buttons at the full Raisely URLs (they are in PLAYBOOK.md section 2).

### GTM/analytics silent after launch

- The new theme must output the GTM container (GTM-K2P27RG) in header and body. Verify with Google Tag Assistant. If missing, ask Claude to add the standard GTM snippets to header.php.

### Something looks wrong only on phones

- Screenshot it with the phone, tell Claude the device and browser. Never launch without the real-phone spot check on the checklist.

## 6. Human-shaped risks (honestly the most likely ones)

- The debugging spiral eats your 1.5 hours. Rule: if you are stuck on one problem for 30 minutes, stop, capture the error and what you tried, end the session. A fresh session with a clean description solves in 10 minutes what a tired spiral doesn't in 60.

- Scope creep. Every "while I'm in here, what if we also..." delays launch. Write the idea in the Phase 2 backlog (PLAYBOOK section 5) and move on. Launching is the feature.

- Content season collision. October is planner-heavy for you. The gate in the plan is the fix: if it slips past 1 November, the answer is February, not rushed testing.

- You are the only one who knows anything. Mitigate now: share the staging URL and this repo location with one other person, and put the SiteGround, WordPress and Raisely logins in whatever password manager FNPW uses, not just your head.

- The old theme or drufloe plugin gets deleted too early. Keep both installed (deactivated is fine) for a full month after launch. They are your rollback.

If a problem isn't in this file, describe it to Claude with: what you did, what you expected, what happened instead, and the exact error text. That sentence structure gets good answers.